## Screens
Screen inventory: what ERPNext offers versus what to build
Verdict: Use ERPNext = admins and finance use the standard Desk; Configure ERPNext = ERPNext handles it, our screen is thin; Build custom = no adequate ERPNext screen. Edit the blue cells to re-plan.
ID | Area | Screen | Main roles | What ERPNext offers | Verdict | Pattern | Device | Offline | Scope | Sprint
P01 | Platform | Login and device registration | All | User, session | Build custom | Form | All | Partial | MVP | S1
P02 | Platform | Role home (task queue) | All | Workspace (too cluttered) | Build custom | Dashboard | All | Cached | MVP | S1
P03 | Platform | Offline and sync tray | All | None | Build custom | List | All | Yes | MVP | S2
P04 | Platform | Notifications | All | Notification | Configure ERPNext | List | All | No | Later | S6
P05 | Platform | Config console (screens, roles, branding) | Admin / IT | None | Build custom | Form | Desktop | No | Later | S10
S01 | Stores (POS) | Till (scan and pay) | Cashier | POS Invoice, POS Profile | Build custom | Scan flow | Tablet | Yes | MVP | S2
S02 | Stores (POS) | Parked sales | Cashier | Draft invoice | Build custom | List | Tablet | Yes | MVP | S2
S03 | Stores (POS) | Shift open and close | Cashier | POS Opening and Closing Entry | Configure ERPNext | Wizard | Tablet | Yes | MVP | S2
S04 | Stores (POS) | Customer lookup | Cashier, Sales rep | Customer | Configure ERPNext | List | Tablet, phone | Cached | MVP | S2
S05 | Stores (POS) | Needs-manager request (discount, void) | Cashier | None | Build custom | Dialog | Tablet | No | MVP | S3
S06 | Stores (POS) | Stock check and order | Sales rep | Item, Bin, Sales Order | Build custom | Scan flow | Phone | Cached | Later | S8
W01 | Web and app | Online orders queue (staff) | Customer success, Delivery | Sales Order, Pick List | Configure ERPNext | List | Desktop | No | Later | S9
W02 | Web and app | Customer app: catalogue, cart, pay, tracking | Customer | Website Item, Shopping Cart | Build custom | Storefront | Phone | No | Later | After S10
W03 | Web and app | Customer scan-and-pay cart with QR | Customer | None | Build custom | Scan flow | Phone | No | Later | After S10
C01 | CRM | Customer accounts | Customer success, Marketing | Customer, Contact | Configure ERPNext | List and detail | Desktop | No | Later | After S10
C02 | CRM | Lead pipeline | Sales rep | Lead, Opportunity kanban | Use ERPNext | Kanban | Desktop | No | Later | After S10
C03 | Customer success | Customer care inbox | Customer success | Issue, SLA | Configure ERPNext | List and detail | Desktop | No | Later | After S10
C04 | Customer success | Feedback follow-up | Customer success | None | Build custom | Form | Desktop | No | Later | After S10
M01 | Marketing | Campaigns and promotions | Marketing | Campaign, Coupon Code, Pricing Rule | Configure ERPNext | List and form | Desktop | No | Later | After S10
M02 | Marketing | Customer segments | Marketing | Weak | Build custom | List | Desktop | No | Later | After S10
M03 | Marketing | Referrals and loyalty | Marketing | Loyalty Program | Configure ERPNext | List | Desktop | No | Later | After S10
D01 | Digital media | Content and prices (price-change request) | Digital media, Marketing | Item, Price List | Configure ERPNext | Form | Desktop | No | Later | After S10
R01 | Procurement | Purchase orders | Procurement officer | Material Request, PO | Configure ERPNext | List and form | Desktop | No | Later | After S10
R02 | Procurement | Supplier onboarding | Procurement officer | Supplier | Configure ERPNext | Form | Desktop | No | Later | After S10
H01 | Warehouse | Goods receipt (scan) | Warehouse officer | Purchase Receipt | Build custom | Scan flow | Tablet | Yes | MVP | S4
H02 | Warehouse | Branch stock request | Branch manager | Material Request | Configure ERPNext | Form | Tablet, phone | No | MVP | S3
H03 | Warehouse | Transfer dispatch (pick and pack) | Warehouse officer | Stock Entry, Pick List | Configure ERPNext | Scan flow | Tablet | Yes | MVP | S4
H04 | Warehouse | Transfer receipt and in-transit list | Branch manager, Warehouse officer | Stock Entry (no signature) | Build custom | Scan flow | Tablet | Yes | MVP | S4
H05 | Warehouse | Stock lookup | Stock roles, Sales rep | Stock Balance | Configure ERPNext | List | Tablet, phone | Cached | MVP | S4
H06 | Warehouse | Quarantine and damaged bin | Warehouse officer | Warehouse | Configure ERPNext | List | Tablet | Yes | Later | S7
K01 | Stock control | Blind cycle count | Stock controller | Stock Reconciliation (not blind) | Build custom | Scan flow | Tablet | Yes | MVP | S4
K02 | Stock control | Variance list and write-off request | Stock controller | None dedicated | Build custom | Approval | Tablet | Partial | MVP | S4
K03 | Stock control | Serial and IMEI check | Stock controller, Cashier | Serial No | Configure ERPNext | Scan flow | Tablet | Yes | Later | S7
T01 | Returns | Customer return (receipt lookup) | Cashier | Sales Return | Configure ERPNext | Wizard | Tablet | Partial | MVP | S3
T02 | Returns | Supplier return | Warehouse officer | Purchase Return | Configure ERPNext | Form | Tablet | No | Later | After S10
T03 | Returns | Returns inspection and restock | Warehouse officer | None | Build custom | Wizard | Tablet | Partial | Later | S7
L01 | Delivery | Dispatch board | Delivery coordinator | Delivery Note, Delivery Trip (basic) | Build custom | Dashboard | Desktop | No | MVP | S4
L02 | Delivery | Rider trips | Rider | None | Build custom | List | Phone | Yes | MVP | S4
L03 | Delivery | Proof of delivery and failed reason | Rider | None | Build custom | Wizard | Phone | Yes | MVP | S4
L04 | Delivery | Rider cash remittance | Rider, Cash controller | None | Build custom | Form | Phone | Partial | MVP | S4
L05 | Delivery | Cash-on-delivery outstanding | Delivery coordinator | None | Build custom | List | Desktop | No | MVP | S4
X01 | Repairs | Repair intake with photos and IMEI | Technician | Warranty Claim (weak) | Build custom | Wizard | Tablet | Partial | Later | S8
X02 | Repairs | My repair jobs | Technician | Custom doctype | Build custom | List and detail | Tablet | Partial | Later | S8
X03 | Repairs | Parts request | Technician | Stock Entry | Configure ERPNext | Form | Tablet | Partial | Later | S8
X04 | Repairs | Quote approval and ready for pickup | Technician, Customer success | None | Build custom | Detail | Tablet, desktop | No | Later | S8
Q01 | Cash-up | Cash-up count | Cashier | POS Closing Entry (partial) | Build custom | Wizard | Tablet | Yes | MVP | S3
Q02 | Cash-up | Cash-up sign-off | Branch manager | None | Build custom | Approval | Tablet, phone | Partial | MVP | S3
Q03 | Cash-up | Cross-branch cash-up review and deposit match | Cash controller | None | Build custom | List | Desktop | No | Later | S7
A01 | Approvals | Approvals inbox | Branch manager, MD, others | Workflow Action, ToDo | Build custom | Approval inbox | Phone, tablet | Queue | MVP | S3
A02 | Approvals | Branch manager home | Branch manager | Reports | Build custom | Dashboard | Tablet, phone | Cached | MVP | S3
A03 | HR and staff | Branch attendance view | Branch manager | Attendance | Configure ERPNext | List | Tablet | No | Later | S6
F01 | Payments | Paystack reconciliation | Accountant | Payment Entry, Bank Transaction | Build custom | List | Desktop | No | Later | S9
F02 | Payments | Payee whitelist | Accountant | None | Build custom | List | Desktop | No | Later | S9
F03 | Payroll | Payout batch (GAPS file, limits, MD code) | Accountant, MD | None | Build custom | Wizard | Desktop, phone | No | Later | S9
F04 | Tax and VAT | VAT and tax returns | Accountant | Tax Template | Build custom | Report | Desktop | No | Later | S9
F05 | Accounting | Bank reconciliation | Accountant | Bank Reconciliation | Use ERPNext | Desk | Desktop | No | Later | Desk
F06 | Accounting | Ledgers and invoices | Accountant | GL Entry, Invoices | Use ERPNext | Desk | Desktop | No | Later | Desk
F07 | Accounting | Journal approval | Accountant, MD | Journal Entry | Configure ERPNext | Approval | Desktop | No | Later | After S10
F08 | Accounting | Branch P and L | MD, Accountant | P and L by Cost Center | Configure ERPNext | Dashboard | Desktop | No | Later | After S10
F09 | Payroll | Payroll runs | HR officer, Accountant | Payroll Entry, Salary Slip | Configure ERPNext | Wizard | Desktop | No | Later | After S10
H10 | HR and staff | Staff records | HR officer | Employee | Use ERPNext | Desk | Desktop | No | Later | Desk
H11 | HR and staff | Leave and attendance (HR) | HR officer | Leave, Attendance | Use ERPNext | Desk | Desktop | No | Later | Desk
H12 | HR and staff | Staff self-service (leave, payslip) | All staff | Employee Self Service | Configure ERPNext | List | Phone | No | Later | After S10
U01 | Audit | Audit trail | Auditor | Version, Activity Log | Configure ERPNext | List | Desktop | No | Later | After S10
U02 | Audit | Audit findings and independent counts | Auditor | None | Build custom | Form | Desktop, tablet | Partial | Later | After S10
G01 | Reporting | Loss report: cash-up variance by branch and cashier | Branch manager, MD | None | Build custom | Dashboard | Tablet, phone | Cached | MVP | S3
G02 | Reporting | Loss report: transfers in transit over 24 hours | Branch manager, MD | None | Build custom | List | Tablet, phone | Cached | MVP | S4
G03 | Reporting | Loss report: unbanked cash and deposit match | Cash controller, MD | None | Build custom | List | Desktop, phone | Cached | Later | S7
G04 | Reporting | Loss report: refunds, voids, discounts by cashier | MD, Auditor | None | Build custom | Dashboard | Desktop | No | Later | S7
G05 | Reporting | Loss report: count variance and write-offs | MD, Auditor | None | Build custom | Dashboard | Desktop | No | Later | S7
G06 | Reporting | Loss report: negative stock and manual adjustments | MD, Auditor | None | Build custom | List | Desktop | No | Later | S7
G07 | Reporting | Loss report: failed deliveries and COD uncollected | Delivery coordinator, MD | None | Build custom | Dashboard | Desktop | No | Later | S7
G08 | Reporting | Loss report: Paystack versus orders | Accountant, MD | None | Build custom | List | Desktop | No | Later | S9
G09 | Reporting | Loss report: price and margin changes | MD, Auditor | None | Build custom | List | Desktop | No | Later | S10
G10 | Reporting | MD morning dashboard | MD | Dashboard, Number Card | Build custom | Dashboard | Phone | Cached | Later | S10
N01 | Admin and IT | Users and roles | Admin / IT | User, Role Permission | Use ERPNext | Desk | Desktop | No | Later | Desk
N02 | Admin and IT | Break-glass admin access (MD-held) | MD | None | Build custom | Form | Desktop | No | Later | S10
P06 | Platform | Print templates (A5 invoice and receipt, statement, delivery note, transfer note) | All | Print Format | Build custom | Template | Desktop, tablet | Partial | MVP | S2
CR01 | Credit sales | Credit sale at till (balance and limit check) | Cashier | Sales Invoice, Customer credit limit | Build custom | Scan flow | Tablet | Partial | MVP | S3
CR02 | Credit sales | Record customer payment against invoices | Cashier, Accountant | Payment Entry | Configure ERPNext | Form | Tablet, desktop | Partial | Later | S6
CR03 | Credit sales | Customer statement (A5 or A4 print) | Credit controller, Customer success | Statement of Account report | Configure ERPNext | Report | Desktop | No | Later | S6
CR04 | Credit sales | Receivables ageing and collections list | Credit controller | Accounts Receivable report | Configure ERPNext | List | Desktop | No | Later | S7
CR05 | Credit sales | Credit limit request and approval | Credit controller, MD | Customer credit limit (no workflow) | Configure ERPNext | Approval | Desktop, phone | No | Later | S7
EX01 | Expenses | Expense request with receipt photo | All staff | Expense Claim | Configure ERPNext | Form | Phone | Partial | Later | S6
EX02 | Expenses | Expense approval (in approvals inbox) | Branch manager, MD | Expense Claim workflow | Configure ERPNext | Approval | Phone | No | Later | S6
EX03 | Expenses | Petty cash float and reconciliation | Cash controller, Branch manager | Journal Entry (no float concept) | Build custom | Wizard | Tablet | Partial | Later | S7
EX04 | Expenses | Company expenses: vendor bills, rent, utilities | Accountant | Purchase Invoice, Journal Entry | Use ERPNext | Desk | Desktop | No | Later | Desk
AS01 | Assets | Asset register and lookup | Accountant, Branch manager | Asset | Configure ERPNext | List and detail | Desktop, tablet | No | Later | After S10
AS02 | Assets | Asset assignment and transfer between branches | Branch manager, Accountant | Asset Movement | Configure ERPNext | Form | Tablet | Partial | Later | After S10
AS03 | Assets | Asset maintenance request and schedule | Branch manager, Technician | Asset Maintenance | Configure ERPNext | Form | Tablet | Partial | Later | After S10
AS04 | Assets | Asset purchase, capitalisation and depreciation | Accountant | Asset, Depreciation Schedule | Use ERPNext | Desk | Desktop | No | Later | Desk
AS05 | Assets | Asset disposal and write-off approval | Accountant, MD | Asset (scrap or sell) | Configure ERPNext | Approval | Desktop, phone | No | Later | After S10
AS06 | Assets | Asset count and verification by scanning tag | Auditor, Stock controller | None | Build custom | Scan flow | Tablet | Yes | Later | After S10

## Sprints
Front-end sprint plan (two-week sprints)
Assumes about 20 productive hours a week for one part-time developer plus Claude Code. Blue cells are inputs. Plan written 31 Oct 2026.
Sprint | Dates | Goal | Delivers | Demo outcome | Planned hours | Screens in sprint
S1 | 2 to 13 Nov 2026 | Foundation | Monorepo, CI, mock server, tenant.json loader, design tokens, app shell, login, permission-driven navigation for 3 roles, offline bar | Log in as 3 roles and see different menus; swap tokens; rebrand from tenant.json | 40 | 2
S2 | 16 to 27 Nov 2026 | Cashier core | Offline queue with idempotency keys, scanner, Till, parked sales, shift open and close, sync tray, A5 invoice and receipt printing through the browser | Ring a sale offline on a tablet, reconnect, see it post once | 40 | 6
S3 | 30 Nov to 11 Dec 2026 | Cash and approvals | Returns, needs-manager request, credit sale at till, approvals inbox, cash-up count and sign-off, manager home, cash-up variance report, stock request | Cashier asks for a discount, manager approves on phone, cash-up shows variance | 40 | 9
S4 | 14 to 25 Dec 2026 | Stock and delivery slice | Goods and transfer receipt, blind count, write-off request, dispatch board, rider trips, proof of delivery, cash remittance, in-transit report | Receive a transfer by scan; rider completes a delivery offline with photo | 40 | 12
Buffer | 28 to 31 Dec 2026 | Handover | Bug fixes, runbook, Storybook, test report, handover session | Second person runs it from the runbook | 10 | 0
S5 | Jan 2027 | ERPNext adapter (reads) | Read adapter against staging ERPNext, contract tests on both adapters | Same screens show real data | 40 | 0
S6 | Jan to Feb 2027 | Adapter writes and pilot hardening | Write adapter, 3G testing, fixes from cashier and rider feedback, notifications, attendance view, customer payments and statements, expense requests and approval | Pilot cashier sells on real back end | 40 | 6
S7 | Feb 2027 | Loss reports and stock extras | Unbanked cash, refunds and voids, count variance, negative stock, failed deliveries, quarantine, returns inspection, serial check, cross-branch cash-up, receivables ageing, credit limits, petty cash | Daily loss report runs for pilot branch | 40 | 12
S8 | Mar 2027 | Repairs and sales rep | Repair intake, jobs, parts, quote; rep stock check and order | Technician logs a repair end to end | 40 | 5
S9 | Mar 2027 | Payments and payouts | Paystack reconciliation, payee whitelist, payout batch, VAT, online orders queue, Paystack report | Payout batch needs MD code | 40 | 6
S10 | Apr 2027 | MD view and config | MD dashboard, price and margin report, break-glass access, config console, design system swap | Second company rebranded from config only | 40 | 4
|  | Total planned hours |  |  | 410
|  | Hours before 31 Dec (S1 to Buffer) |  |  | 170
Note: about 8.5 weeks (roughly 170 hours) remain before 31 Dec 2026, so only S1 to S4 plus a handover buffer fit. S5 onward needs a continuing owner.

## Summary
Summary (updates when the Screens tab changes)
Verdict | Screens | Of which MVP
Use ERPNext | 8 | 0
Configure ERPNext | 35 | 6
Build custom | 50 | 23
Total | 93 | 29
Note: the product manager's MVP list included unbanked cash; it is placed in S7 here because it needs deposit data from the back end.